roam.

adventure matching

MVP BUILD ROADMAP

Complete technical specification · Blue Maunga Limited · 2025

# 1. Where We Are Now

The following screens are built and working as interactive React prototypes:

- Discover screen — cinematic match cards with adventure DNA overlap meter, Almost Met alert, photo strip

- Upload screen — live Claude Vision AI photo screener with person detection, authenticity scoring, manipulation flagging, and auto adventure tagging

- Matches screen — match list with shared tag display and overlap percentage

- Signup flow — 3-step account creation with tier selection, photo licensing consent, and required/optional checkbox system

Design tokens are locked: Playfair Display / DM Mono / Outfit typefaces, forest-dark palette (#0E1A0D), electric green accent (#C8E64A), topographic grid background. All future screens must inherit these tokens.

Status We have a high-fidelity prototype covering ~60% of MVP scope. The AI vision layer, design system, and monetisation logic are done. What remains is backend plumbing, routing, and the matching engine.

# 2. What Remains — Ordered Build List

Do these in order. Each step unlocks the next. Do not skip ahead.

## Phase 1 — Foundation (Week 1–2)

Nothing works without this. Do it first.

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 1.1 | Project scaffold | Vite + React + TypeScript. Install React Router v6, Tailwind, Axios. | Runnable shell app |
| 1.2 | Design token file | Create tokens.css with all CSS variables from prototype. Import globally. | Locked visual identity |
| 1.3 | Route structure | React Router: /, /signup, /onboarding, /discover, /upload, /matches, /profile, /settings | Navigation skeleton |
| 1.4 | Supabase project | Create project at supabase.com. Enable Auth, Storage, Realtime. Copy env keys. | DB + auth + storage live |
| 1.5 | Auth — signup | Wire signup form to supabase.auth.signUp(). Store user row in users table on confirm. | Real accounts created |
| 1.6 | Auth — login | supabase.auth.signInWithPassword(). Persist session. Protected route wrapper. | Login works |
| 1.7 | Auth — Google OAuth | Enable Google provider in Supabase dashboard. One-tap login button. | Social login |
| 1.8 | DB schema | Run migrations: users, photos, tags, matches, messages, bucket_list tables. See schema below. | Data model live |

## Phase 2 — Photo Pipeline (Week 2–3)

This is the core product differentiator. The AI tagging engine is what makes ROAM different from every other app.

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 2.1 | Photo upload UI | File input on Upload screen. Preview selected image before submitting. | User can pick photos |
| 2.2 | Upload to Supabase Storage | supabase.storage.from('photos').upload(). Get public URL back. | Photos stored in cloud |
| 2.3 | Claude Vision API call | POST to /api/analyse. Pass public URL to Claude claude-sonnet-4-20250514 with moderation prompt. Return JSON. | AI screens photo |
| 2.4 | Store AI result | Save to photos table: person_score, authenticity_score, adventure_score, tags[], verdict. | Tags stored |
| 2.5 | Show result to user | Render meter bars, verdict banner, and auto-tags on upload screen in real time. | User sees screening result |
| 2.6 | Rejection flow | If verdict = rejected_*, show reason message. Delete from storage. Do not save to profile. | Bad photos blocked |
| 2.7 | Profile photo order | Sort by person_score DESC on profile display. Photos with person show first. | Best content leads |

## Phase 3 — Matching Engine (Week 3–4)

The algorithm is simple: tag overlap score weighted by tag rarity. Build it as a Postgres function first, then wrap in a Node worker.

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 3.1 | Tag vector per user | Aggregate all approved photo tags into a tags[] array per user in the users table. | Each user has a fingerprint |
| 3.2 | Overlap scoring function | Postgres function: count shared tags / total unique tags. Boost rare tags. | overlap_score(user_a, user_b) |
| 3.3 | Match generation worker | Node cron job (runs every 15 min): for each new user, score against all others. Write top 50 to matches table. | Matches generated |
| 3.4 | Fetch matches for Discover | GET /api/matches — return paginated match list with overlap score and shared tags. | Discover screen is live |
| 3.5 | Swipe actions | POST /api/matches/:id/pass or /like. When both like, set status = matched. | Mutual matching works |
| 3.6 | Almost Met engine | Compare photo geotags (EXIF or user-tagged location) + timestamp. If within 50km + 60 days, flag. | Almost Met alert fires |

## Phase 4 — Messaging (Week 4–5)

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 4.1 | Messages DB table | id, match_id, sender_id, content, created_at. Index on match_id. | Schema ready |
| 4.2 | Supabase Realtime | Subscribe to messages channel per match_id on component mount. | Live message feed |
| 4.3 | Send message | POST /api/messages. Insert row. Realtime pushes to recipient. | Sending works |
| 4.4 | Message thread UI | New screen: /messages/:matchId. Bubble layout, timestamps, avatar. | Chat screen done |
| 4.5 | Matches screen link | Tap a match row → navigate to /messages/:matchId. | Navigation wired |
| 4.6 | Push notifications | Supabase Edge Function triggers Resend email on new message if user offline. | User notified |

## Phase 5 — Bucket List (Week 5–6)

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 5.1 | Destination picker | Search input autocomplete via Mapbox Places API. Store as destination_name + lat/lng. | User can add destinations |
| 5.2 | Bucket list screen | Grid of pinned destinations with match count badge. | Bucket list UI live |
| 5.3 | Destination match query | Find users with same destination_name. JOIN with matches. Surface in Discover. | Bucket list matching |
| 5.4 | Notification | When a match pins the same destination you have, send email via Resend. | Engagement loop active |

## Phase 6 — Payments & Tiers (Week 6)

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 6.1 | Stripe setup | Create products: Explorer (free), Adventurer ($12/mo), Adventurer Annual ($99/yr). | Stripe products live |
| 6.2 | Checkout flow | Stripe Checkout session. Redirect to /settings on success. | Payment works |
| 6.3 | Webhook handler | POST /api/stripe/webhook. On checkout.session.completed, update user tier in DB. | Tier upgrades correctly |
| 6.4 | Tier enforcement | Middleware checks user.tier before returning messaging / Bucket List / Almost Met data. | Free limits enforced |
| 6.5 | Contributor flow | On Contributor signup, store photo_licence_agreed = true. Flag photos as licensable. | Licence captured |

## Phase 7 — Onboarding Polish (Week 7)

| Step | What | How / Tools | Output |
| --- | --- | --- | --- |
| 7.1 | Onboarding wizard | After signup: prompt to upload first 6 photos. Show progress bar. Block Discover until 3 photos pass AI screening. | New users have content |
| 7.2 | Adventure type quiz | 5-question onboarding quiz: urban/wilderness/coastal/festival/foodie. Seeds initial tags before first photo upload. | Cold start solved |
| 7.3 | Empty state handling | If no matches yet, show &#x201C;your profile is being matched&#x201D; with tips to add more photos. | No blank screens |
| 7.4 | Profile edit screen | User can reorder photos, delete photos, edit bio tagline, update location. | Profile is editable |

# 3. Database Schema

Run these as Supabase SQL migrations in order.

users

- id (uuid PK), email, name, dob, gender, location_text, lat, lng

- tier (enum: free | adventurer | contributor), tier_expires_at

- photo_licence_agreed (boolean), adventure_tags[] (text[])

- created_at, last_active_at

photos

- id, user_id (FK), storage_url, thumbnail_url

- person_score, authenticity_score, adventure_score (integers 0-100)

- verdict (enum: approved | needs_person | rejected_quote | rejected_manipulated | rejected_stock)

- tags[] (text[]), manipulation_flags[] (text[])

- is_licensable (boolean), photo_lat, photo_lng, photo_taken_at

- display_order (integer), created_at

matches

- id, user_a_id, user_b_id, overlap_score (float), shared_tags[] (text[])

- status (enum: pending | liked_a | liked_b | matched | passed)

- almost_met_location (text), almost_met_date (date)

- created_at, matched_at

messages

- id, match_id (FK), sender_id (FK), content (text), created_at

bucket_list

- id, user_id (FK), destination_name, lat, lng, created_at

# 4. Full Route Map

| Route | Access | Screen |
| --- | --- | --- |
| / | Public | Landing page — hero, value prop, App Store links |
| /signup | Public | 3-step signup: account details, tier selection, consents |
| /login | Public | Email/password + Google OAuth |
| /onboarding | Auth required | Photo upload wizard — minimum 3 approved photos before proceeding |
| /discover | Auth + photos | Match cards — swipe / pass / roam together |
| /upload | Auth required | Photo management — upload, AI screen, reorder, delete |
| /matches | Auth required | List of mutual matches with overlap tags |
| /messages/:matchId | Auth + matched | Real-time chat thread between matched users |
| /bucket-list | Auth required | Add / view destination wishlist, see match count per place |
| /profile | Auth required | Own profile view — how others see you |
| /profile/:userId | Auth required | Another user&#x2019;s profile — called from messages thread |
| /settings | Auth required | Tier management, payment, notification prefs, photo licence toggle |
| /settings/billing | Auth required | Stripe customer portal — upgrade, downgrade, cancel |
| /admin/photos | Admin only | Moderation queue — photos flagged for human review |
| /admin/licences | Admin only | Browse licensable contributor photos by tag |

# 5. Technology Stack

| Layer | Technology | Notes |
| --- | --- | --- |
| Frontend | React + Vite | TypeScript, Tailwind CSS, React Router v6 |
| Backend API | Node.js + Express | REST + WebSockets for messaging |
| Database | PostgreSQL | Supabase (managed — auth + DB + storage in one) |
| Auth | Supabase Auth | Email/password + Google OAuth |
| Photo storage | Supabase Storage / S3 | Pre-signed URLs, CDN delivery via Cloudflare |
| AI screening | Claude claude-sonnet-4-20250514 | Vision API — person detection, tags, manipulation |
| Geo matching | PostGIS | Extension on Postgres — geotag overlap queries |
| Matching engine | Node.js worker | Tag vector overlap scoring, cron-triggered |
| Messaging | Supabase Realtime | WebSocket channels per match pair |
| Payments | Stripe | Subscriptions + webhook for tier upgrades |
| AI agents | OpenAI Agents SDK / LangGraph | Moderation pipeline, photo tagging batch jobs |
| Hosting | Railway or Fly.io | Backend; Vercel or Netlify for frontend |
| Email | Resend | Transactional — match alerts, Almost Met, Bucket List |

Why Supabase? Supabase gives you Postgres + auth + file storage + realtime WebSockets in one managed service. For an MVP this eliminates 3 separate infrastructure decisions. You can migrate any component later once you know what needs scaling.

# 6. AI Agent Architecture

Three agent pipelines run the app intelligently. Two are background workers; one is user-facing.

## Agent 1 — Photo Moderation Agent (background)

Runs on every photo upload. Already partially built in the prototype.

- Trigger: photo uploaded to Supabase Storage

- Action: call Claude Vision API with moderation prompt

- Output: JSON scores + tags written to photos table

- If authenticity_score < 40: flag for human review queue at /admin/photos

- If person_score < 30: set verdict = needs_person, lower display_order

- If isQuoteOrText = true: hard reject, delete from storage, notify user

- Tool: Claude claude-sonnet-4-20250514 via Anthropic API

## Agent 2 — Matching Agent (background cron)

Runs every 15 minutes as a Node.js worker. Scores all new users against existing pool.

- Step 1: SELECT users where last_active_at > NOW() - INTERVAL 7 days

- Step 2: For each user pair not yet scored, call overlap_score() Postgres function

- Step 3: Insert top 100 candidates per user into matches table with overlap_score and shared_tags

- Step 4: Run Almost Met query — PostGIS ST_DWithin(50km) + timestamp overlap on photo geotags

- Step 5: Send email via Resend if a new Almost Met is found

- Tool: Node cron (node-cron), PostGIS, Resend API

## Agent 3 — Licence Brokering Agent (admin-triggered)

This is the commercial photo licensing pipeline. Run it on demand from /admin/licences.

- Query: SELECT photos WHERE is_licensable = true AND verdict = approved ORDER BY adventure_score DESC

- Cluster by dominant tag (alpine hiking, surf, street food etc.)

- Claude generates a pitch pack: tag summary, photo count, sample URLs, suggested price per image

- Output: PDF brief emailed to pre-loaded list of brand contacts (Kathmandu, Tourism NZ, etc.)

- On sale: record in licence_sales table, trigger royalty payment if sale > $200 NZD via Stripe

- Tool: Claude claude-sonnet-4-20250514 (text), Anthropic API, Stripe, Resend

OpenAI Agents SDK / LangGraph note You can wire agents 1 and 2 as LangGraph graphs if you want human-in-the-loop review steps, retries on API failures, and observable traces. For MVP the simpler direct API calls are fine. Upgrade to LangGraph when you need audit trails for the licensing pipeline.

# 7. Monetisation

| Plan | Price | Features | Purpose |
| --- | --- | --- | --- |
| Explorer (Free) | $0 | 9 photos, see matches, 3 connections/mo | Acquisition |
| Adventurer | $12 NZD/mo | Unlimited uploads, full messaging, Bucket List, Almost Met | Core revenue |
| Contributor | Free | Adventurer access in exchange for photo licence | Data asset + retention |
| Adventurer Annual | $99 NZD/yr | 2 months free vs monthly | LTV boost |

## Photo Licensing Revenue Stream

This is the sleeper asset. As the contributor base grows, ROAM accumulates a curated, AI-tagged adventure photo library. Every photo is tagged with specific adventure types, locations, and demographic signals (derived from profile data, never personally identifying).

- Target buyers: Tourism NZ, Destination Queenstown, Kathmandu, Macpac, surf brands, boutique hotels

- Pitch: authentic UGC outperforms stock 3:1 in ad click-through. Your library is GPS-verified, person-present, AI-tagged.

- Pricing model: $50-150 NZD per image for web/social licence. $300+ for exclusive editorial.

- Royalty split: 30% to contributor, 70% to ROAM. Paid via Stripe on sale confirmation.

- Contributor receives email: \u201CYour photo of Milford Sound was licensed to Tourism Southland for $120 NZD. Your cut: $36 NZD has been paid.\u201D

## Destination Partner Revenue

- Adventure operators (kayak tours, climbing guides, surf schools) pay to appear as sponsored experiences in Bucket List

- When 2 matched users both pin Queenstown, a Remarkables ski ad can surface \u2014 relevant, not intrusive

- Estimated $500-2000 NZD/mo per destination partner at scale

# 8. Timeline to Launch

| Week | Phase | Milestone |
| --- | --- | --- |
| 1-2 | Foundation | Scaffold, Supabase, auth, DB schema, protected routes — app navigates |
| 2-3 | Photo pipeline | Upload works, Claude Vision screens in real time, tags stored, rejected photos blocked |
| 3-4 | Matching engine | Discover screen shows real matches with real overlap scores, Almost Met fires |
| 4-5 | Messaging | Matched users can chat in real time |
| 5-6 | Bucket List + Stripe | Destination matching live, payments work, tier enforcement active |
| 7 | Onboarding polish | Wizard, quiz, empty states, profile edit — app feels complete |
| 8 | Closed beta | 50 hand-picked NZ users. Collect feedback. Fix critical bugs. |
| 10 | Public launch | App Store + Play Store (via Capacitor or React Native wrapper), Product Hunt |

# 9. What to Build Next in This Session

In order of impact, the next screens to prototype before the token limit:

- Onboarding wizard — the photo upload flow with AI screening wired live

- Messaging thread screen — bubble UI for /messages/:matchId

- Profile screen — how your photos and tags appear to matches

- Settings / billing screen — tier display, upgrade CTA, contributor toggle

- Landing page — public-facing hero for acquisition (App Store link, value prop, 3 example match stories)

Recommendation Build the onboarding wizard next. It is the most critical user journey — if first-time users don&#x2019;t get 3 photos through the AI screener in their first session, they never come back. Getting this flow right is more important than any other screen.